## Issue-Log
ISSUE MANAGEMENT LOG
Project Name:
ID | Status | Serverity | Priority | System / Function | Issue Description | Impact | Actions | Escalation Needed (Y/N)? | Date Identified | Estimated Resolution Date | Logged By | Actual Completion Date | Final Resolution & Follow-on actions
1 | Open | N/A | N/A |  | Issues raised by board members about the business case are preventing the project moving out of the initiation stage. | Potential project cancellation or significant delay. | Meet with board members to review the business case and revise the investment appraisal if needed. | -
2 | Work In Progress | N/A | N/A |  | The project is missing a system architect. | Delay to start of project design phase. | Recruit a System Architect | -
3 | Closed | N/A | N/A |  | Availability of human resources doesn't match the project resource plan. | May be forced to level the plan to fit resource availability which will delay target go live date. | Meet with department heads to review resource plans and re-prioritise work. | -
4 |  | N/A | N/A
5
6
7
8
Note on A5: A unique ID number for refference to an issue.
Note on B5: Status: - Open: The issue is currently open but has not yet been resolved. - Work In Progress: The issue is being actively worked to develop a resolution. - Closed: The issue is no longer considered an active project threat and can be closed with or without resolution.
Note on C5: Critical, High, Medium, Low. Critical: Issue will stop project progress. High: Issue will likely impact budget, schedule or scope. Medium: Issue impact the project, but could be mitigated to avoid an impact on budget, schedule or scope. Low: Issue is low impact and/or low effort to resolve.
Note on D5: High, Medium, Low. High: Need to resolve this issue as soon as possible. Medium: If doesn't have any high-priority task, this task should be in the next. Low: After any task cleared already, this task should be resolved.
Note on E5: Estimated or target date for completion of actions.
Note on F5: Give a brief description of the issue.
Note on G5: Describe the impact of the issue. This may be in terms of the project constraints of time, cost and scope.
Note on H5: Actions to mitigate the issue, avoid the issue, or resolve the issue.
Note on I5: “Yes” if the program/project manager feels an issue needs to be escalated and “No” if escalation is not needed to resolve the issue.
Note on J5: The date that the issue was identified.
Note on K5: Estimated or target date for completion of actions.
Note on M5: Actual completion date.
Note on N5: Document the outcome. Is the issue resolved and if so how? Are there any follow-on actions? Are there any follow-on risks?

## data-source
Issue Severity | Description
Critical | Issue will stop project progress.
High | Issue will likely impact budget, schedule or scope.
Medium | Issue impact the project, but could be mitigated to avoid an impact on budget, schedule or scope.
Low | Issue is low impact and/or low effort to resolve.
N/A | No Answer.
Issue Priority | Description
High | Need to resolve this issue as soon as possible.
Medium | If doesn't have any high-priority task, this task should be in the next.
Low | After any task cleared already, this task should be resolved.
N/A | No Answer.
System or Function | Description
System 1 | This system related about …...

## Change History
Document Control Version | [5 empty] | Version 1.00 © Greenline Synergy Co., Ltd.
Change History
| Date | Name | Role | Description | Version
| 2024-05-19 | Chakrit Salaeman | Tester | Creat Documentation Template | 1